## Index
Page Index | Description
1 | Home Route
2 | Restaurant View
3 | Category View
4
5
6
7
8
9
10
11

## Home
Page Title | Home view
Order | 1
Route | "/"
Sl.No | Features | Status | ETC | Comments
1 | Header | Done
2 | Left Menu | Done
3 | ShareLocaton | WIP |  | Need to talk on functionality
4 | Search Functionality | Done
5 | Google maps integration | Done
6 | Location list item components | Done
7 | Location list item component - slide | Done
8 | Custom Location Icons | Done |  | Not available with required formats
9 | Footer | Done
10 | Page level styles | Done
11 | Add Restaurant - | WIP |  | Need to talk on functionality
12 | Join BitGate | WIP |  | Need to talk on functionality
Required Assets :
Font Assets
icons- svg / sprites
cart icon

## Restaurant View
Page Title | Restaurant View
Order | 2
Route | "/restaurant
Sl.No | Features | Status | ETC | Comments
1 | Categort - api service - angular | WIP | 2016-06-18 | Service url is required
2 | Restaurant Hours - api service - angular | WIP | 2016-06-18 | Service url is required
3 | Delivery Hours - api service - angular | WIP | 2016-06-18 | Service url is required
4 | Category list overlay - directive | WIP | 2016-06-18
5 | Category component - directive | WIP | 2016-06-18
6 | Category list scroll component | WIP | 2016-06-25
7 | Category dropdown directive | WIP | 2016-06-25
8 | Restaurant Hours | WIP | 2016-06-25 | Need to talk
9 | Delivery Hours | WIP | 2016-06-25 | Need to talk
10 | Page styles | WIP | 2016-06-25
Required Assets
Category Images
Icons shown in comps
Font assets

## Category View
Page Title | Category View
Order | 3
Route | "/categoryName"
Sl.No | Features | Status | ETC | Comments
1 | Items List service - angular | Wip | 2016-07-02 | Rest service is required
2 | Items list Dropdown | Wip | 2016-07-02
3 | Items list menu - directive | Wip | 2016-07-02
4 | Item component - directive | Wip | 2016-07-02
5 | Item List controll integration | Wip | 2016-07-02
6
7
8
9
10
11
12
Required Assets
Icons shown in comps
Font assets